## Feb 2026
SR# | Activity | Status | Category | Delivery Date | Assigned To | Comments
1 | SUNDAY
2 | Switched to LDMS, Working on Reporting Section: (1) Headers - Geographical, Departments, Schemes and PLD wise | Ongoing | LDMS | 2026-02-06 | Ayush M Srivastava | Validation setup and hardening of TMS pending.
3 | On leave due to Family Emergency
4 | Switched to LDMS, Working on Reporting Section: (1) Headers - Working on Scheme Code bug, Support bucket and Date filters. (2) Body - Report table and Excel-Export Button | Ongoing | LDMS | 2026-02-06 | Ayush M Srivastava | Validation setup and hardening of TMS pending.
5 | Switched to setup for Staging server provided by the Department for Hosting and security audit, (1) Migration of Test DB, with the exact collation and schema as the real one. | Ongoing | Staging Server Setup | 2026-02-12 | Ayush M Srivastava | Reporting Section of LDMS Pending, Validation setup and hardening of TMS pending.
6 | Switched to setup for Staging server provided by the Department for Hosting and security audit, (1) Setup of Backend - Django (python) connected to localhost Test DB (2) Exposing APIs for Auth and TMS | Ongoing | Staging Server Setup | 2026-02-12 | Ayush M Srivastava | All other project development on hold, as staging server setup on priority
7 | Switched to setup for Staging server provided by the Department for Hosting and security audit, (1) Hosting TMS frontend on new server and setting up environment variables | Ongoing | TMS | 2026-02-12 | Ayush M Srivastava | All other project development on hold, as staging server setup on priority
8 | Switched to setup for Staging server provided by the Department for Hosting and security audit, (1) Locking Hosts for audit ready API and enforcing key based API protection. | Ongoing | TMS | 2026-02-12 | Ayush M Srivastava | All other project development on hold, as staging server setup on priority
9 | Switched to setup for Staging server provided by the Department for Hosting and security audit, (1) Fixed filter headers for batch list module in TMS (2) Added object layer protections for restricted access aside from frontend | Ongoing | TMS | 2026-02-12 | Ayush M Srivastava | All other project development on hold, as staging server setup on priority
10 | Switched to setup for Staging server provided by the Department for Hosting and security audit, (1) Created and linked tables for audit and logging of different API requests being hit from different IP addresses | Completed | TMS | 2026-02-12 | Ayush M Srivastava | All other project development on hold, as staging server setup on priority
11 | Switched to setup CRP-EP App for Staging server, (1) Analysis of Suksham Udhyam Sakhi App, (2) Enterprise forms and identification of fields currently leaking from API | Completed | Suksham Udhyam Sakhi App | 2026-02-11 | Ayush M Srivastava | Received Internal Security Audit report of TMS, now working on fixing vulnerabilities
12 | Switched to setup CRP-EP App for Staging server, (1) Updation of old Enterprise (Existing and New) APIs with creation of new APIs (changes: Mandatory Fund, Licenses, Shop, Segregated Media (Shop, Products and Enterprise Media) | Ongoing | Suksham Udhyam Sakhi App | 2026-02-16 | Ayush M Srivastava | Worked on Captcha implementation (frontend) in TMS based on vulnerabilities observed in Internal Audit report
13 | Switched to setup CRP-EP App for Staging server, (1) Creation of new Child Tables for Mandatory Fund, Licenses, Shop, and Segregated Media (Shop, Products and Enterprise Media) | Ongoing | Suksham Udhyam Sakhi App | 2026-02-16 | Ayush M Srivastava | Worked on IDOR error in TMS based on vulnerabilities observed in Internal Audit report
14 | Compensatory leave due to office work on Sunday (08-02-26)
15 | SUNDAY
16 | Switched to setup CRP-EP App for Staging server, (1) Creation of new Child APIs for Mandatory Fund, Licenses, Shop, and Segregated Media (Shop, Products and Enterprise Media) | Completed | Suksham Udhyam Sakhi App | 2026-02-16 | Ayush M Srivastava | CRUD (Create/Read/Update/Delete) APIS for Each Child Tables - Mandatory Fund, Licenses, Shop, and Segregated Media (Shop, Products and Enterprise Media)
17 | Switched to setup CRP-EP App for Staging server, (1) Creation of Admin Panel with proposed Admin Functions (User Account Management, Panchayat Assignement, and Basic Analytics) | Ongoing | Suksham Udhyam Sakhi App | 2026-02-20 | Ayush M Srivastava | Creation of Developer's response of TMS based on vulnerabilities observed in Internal Audit report
18 | Switched to setup CRP-EP App for Staging server, (1) Resolving bugs related to CRP List and Filters, (2) Finalizing Admin Dashboard | Ongoing | Suksham Udhyam Sakhi App | 2026-02-20 | Ayush M Srivastava | Creation of Developer's response of TMS based on vulnerabilities observed in Internal Audit report
19 | Switched to setup CRP-EP App for Staging server, (1) Creation of Admin - CRP View Module with Full CRP profile (2) CRP-EP Account details fetching | Ongoing | Suksham Udhyam Sakhi App | 2026-02-20 | Ayush M Srivastava | Creation of CRP User Account fields and profile form with updation button, and modifying the crp-profile api from read-only to support CRUD operations
20 | Switched to setup CRP-EP App for Staging server, (1) Extending CRP View Button with Assigned Panchayat fetching (2) Creation of updation of Assigned Panchayats from Admin side | Completed | Suksham Udhyam Sakhi App | 2026-02-20 | Ayush M Srivastava | Creation of CRP-Panchayat rows with change button and delete icon with drop downs of districts, their subsequent blocks and their panchayats
21 | Switched to setup CRP-EP App for Staging server, (1) Updation of New Enterprise form with updated API structure and form fields, (2) Updation of Android app on Staging Server. | Ongoing | Suksham Udhyam Sakhi App | 2026-02-24 | Ayush M Srivastava | Received External Security Audit report of TMS, now working on fixing vulnerabilities
22 | SUNDAY
23 | Switched to setup CRP-EP App for Staging server, (1) Setup of EPSMS DB Tables (2) Population of Test CRP Accounts and their mapped Panchayats | Ongoing | Suksham Udhyam Sakhi App | 2026-02-24 | Ayush M Srivastava | Migration of Test EPSMS DB Snapshot with schema and creation on staging server DB, created DB Indexes of related tables and merged with Django models in Backend
24 | Switched to setup CRP-EP App for Staging server, (1) Exposing APIs from staging server and imposing security rules (2) Updating Android App backend keys to match with staging server | Completed | Suksham Udhyam Sakhi App | 2026-02-24 | Ayush M Srivastava | Migration of Backend views, serializers and urls of EPSMS dev-backend to staging server and testing of APIS. Creation of Android package of Completed App ready for Round 1 Security Audit.
25 | Switched to TMS on Staging server, (1) Implementation of Server side Captacha and session validation (2) Working on Business layer validations in Contact Person creation form. | Ongoing | TMS | 2026-02-26 | Ayush M Srivastava | Creation and planning of Client Requirements report based on security parameters and other limiting factors(Otp gateway, etc.)
26 | Switched to TMS on Staging server, (1) Worked on configuring Pragma X-HTTP Headers (2) Worked on Audit tables and optimizing cache services | Completed | TMS | 2026-02-26 | Ayush M Srivastava | Creation and planning of Client Requirements report based on security parameters and other limiting factors(Otp gateway, etc.)
27 | Switched to LDMS, (1) Worked on Support Mapping Form and its APIs (2) Worked on created_by field not registering in child tables of form | Ongoing | LDMS | 2026-02-28 | Ayush M Srivastava | Creation and planning of Client Requirements report based on security parameters and other limiting factors(Otp gateway, etc.)
28 | Switched to LDMS, (1) Worked on creation of Lucknow's Map for dashboard. (2) Worked on optimizing cache of LDMS API response | Completed | LDMS | 2026-03-09 | Ayush M Srivastava | Creation and planning of Client Requirements report based on security parameters and other limiting factors(Otp gateway, etc.)