## Feb 2026
SR# | Activity | Status | Category | Delivery Date | Assigned To | Comments
1 | Sunday
2 | Worked on the lable Translation feature of the existing form - basic info , investment details , product and services sections. | completed | Enterprise sakhi app | 2nd feb | Haripriya | rest of the sections out of the nine sections are ongoing
3 | Enterprise app presentation - SIDC training center. | completed | Enterprise sakhi app | 3rd feb | Haripriya | whole day training 2 batch
4 | lokos down, worked on UI part of the EP sakhi app. | completed | Enterprise sakhi app | 4th feb | Haripriya | worked on updating UI of the CRP app login
5 | lokos down, worked on UI part of the EP sakhi app. | completed | Enterprise sakhi app | 5th feb | Haripriya | worked on updating UI of the CRP app dashboard
6 | On leave due to personal reasons
7 | Worked on TMS featres completion. | completed | TMS | 7th feb | Haripriya | worked on contact person creation & updation and validations in the field
8 | Worked on TMS featres completion. | completed | TMS | 8th feb | Haripriya | worked on training request list module feature (adding filter options) & worked on bug fixing
9 | Worked on TMS featres completion. | completed | TMS | 9th feb | Haripriya | Worked on Validations for capuring batch attendence if deadline missed (mark all as absent).
10 | Worked on TMS featres completion. | completed | TMS | 10th feb | Haripriya | worked on fixing create batch feature and worked on bug fix & worked on login page validations & captcha module.
11 | Worked on CRP-EP App- Worked on the CRP EP app to analyze fields whose data is not being recorded in the backend database, and identified new fields that need to be added to the backend. | completed | CRP_EP | 11th feb | Haripriya | Analyzed the CRP EP application to identify fields not saving data in the backend DB and reviewed new backend field requirements.
12 | Worked on CRP-EP App- Worked on the language conversion part of the Existing Form module, specifically in the Investment Details section and Loan & Subsidy Details section, including the loan and subsidy components. | completed | CRP_EP | 12th feb | Haripriya | Implemented language conversion in the Existing Form module, covering the Investment Details section and the Loan & Subsidy Details section, including all related loan and subsidy components.
13 | Worked on CRP-EP App- Worked on the language conversion implementation in the Existing Form Module, specifically in the Training & Skill Section. Implemented bilingual support in the following sections: Support Required section Media section Declaration & Submit section View Recorded Beneficiary section Error message handling Translation mapping, conditional rendering based on selected language | completed | CRP_EP | 13th feb | Haripriya | Bilingual (language toggle) integration in the Existing Form Module. Extended language conversion support to the following modules: Support Required section Media upload section Declaration & Submission section View Recorded Beneficiary section Validation and error messages Ensured all labels, placeholders, buttons, and validation messages dynamically switch based on the selected language.