Monthly Progress Report (MPR)

Ref no.- BDO/MPR/02/2025-26						Date:31/Oct/2025

Client: UPSRLM

Title: Digital System Assessment & Planning Phase (As-Is Study & FRS Development)

Work order no: UPLC:SW:3108:2025-2026):1369:2536  Dated 19/08/2025

Period –From 1st Oct 2025 – 31st Oct 2025

Tasks/Activities Undertaken: -

| Oct-25 |  |  |
| --- | --- | --- |
| Date | Task Details | Status |
| 1 | Conducted a client meet to follow up regarding the Staging server status | Team working on initial draft for FRS of CRP-EP, 1) Structuring requirements for fields to be included in enterprise forms for DIDIs having existing enterprises. |
| 2 | Conducted a client meeting with ‘Enterprise Promotion’ Thematic experts for resolution of doubts regarding fields for “existing enterprise” form | Team recorded inputs and now working on additions of more fields in the form and extending the FRS of CRP-EP App |
| 3 | Conducted internal strategy meet regarding updates received in recent meet with client | Team working on initial draft for FRS of CRP-EP, 1) Adding scope for fields for New Enterprise form 2) Making other changes related to integration with LokOS |
| 4 | Conducted a client meeting with ‘Enterprise Promotion’ Thematic experts for resolution of doubts regarding drop-down related input processing in the app (Most of the inputs should be selected from drop-downs) | Team working on initial draft for FRS of CRP-EP, 1) Extending scope for enterprise form management to fit client’s requirements. 2) Consolidation of income monitoring related requirements |
| 5 | SUNDAY |  |
| 6 | Conducted internal review of FRS of CRP-EP App and gave inputs regarding changes in Availability and Resilience | Team working on changes recorded in FRS review meet of CRP-EP App, 1) Addition of requirements for Offline data saving capability. 2) Addition of requirements for Automated data synchronization. |
| 7 | Conducted a client meeting with ‘Enterprise Promotion’ Thematic experts for resolution of doubts regarding drop-down related input processing in the app (Most of the inputs should be selected from drop-downs) | Team working on initial draft of FRS for CRP-EP App, 1) Highlighting All didis across the app, who are PLDs. 2) Integration of data from data capture app to Combined dashboard. |
| 8 | Finalized FRS of all approved modules, and prepared for review. | Team working on High Level and Workflow diagrams for approved modules, - BMS - TMS - CRP-EP App |
| 9 | Client Meeting regarding review of FRS document for all approved modules, - Beneficiary Management System - Training Management System - Enterprise Sakhi Management System | Team started working on SRS for all approved modules, - BMS - TMS - CRP-EP App |
| 10 | Conducted internal strategy meet regarding updates received in recent meet with client | Team working on SRS for module- Beneficiary Management System, 1) Planning Database design 2) Creation and structuring of ER-Diagram |
| 11 | Conducted internal strategy meet to plan creation for SRS of approved modules, - BMS - TMS - CRP-EP App | Team working on SRS for module- Beneficiary Management System, 1) Structuring and aligning System Context 2) Deciding Design and implementation constraints |
| 12 | SUNDAY |  |
| 13 | Conducted a client meeting with ‘IT’ Thematic experts for resolution of doubts regarding LokOS data headers. | Team working on SRS for module- Beneficiary Management System, 1) Structuring and creating LokOS Data flows 2) Alignment of Functional Requirements with software 3) Finalizing SRS for BMS |
| 14 | Conducted internal review for SRS of Beneficiary Management System | Team started working on SRS for module- Training Management System, 1) Alignment of High-Level System Features 2) Structuring Use Cases and Sequence/Activity diagrams |
| 15 | Conducted a client meeting with ‘Training Management’ Thematic experts for resolution of doubts regarding information fields for training partner centre registration | Team working on SRS for module- Training Management System, 1) Creation of Complete DFDs and Structure of workflows 2) Creation of Complete Data Dictionary |
| 16 | Conducted a client meeting with ‘Training Management’ Thematic experts for resolution of doubts regarding Mixed Batches (Participants from Multiple Blocks combined in 1 batch) | Team working on SRS for module- Training Management System, 1) Creation of RTM and alignment with all other Non-functional requirements. 2) Finalized SRS for TMS |
| 17 | Conducted internal review for SRS of Training Management System | Team working on SRS for module- CRP – EP App, 1) Creation of complete Data Dictionary 2) Creation of Complete DFDs and Structure of Workflows 3) Alignment of Role-base authorization and Non-functional requirements |
| 18 | Client Meeting regarding review of SRS document for all approved modules, 1. Beneficiary Management System 2. Training Management System 3. Enterprise Sakhi Management System | Team started working on PoC for module- Beneficiary Management System, 1) Creation of HTML based UI Wireframe design of pages 2) Structuring of all system diagrams and flowcharts related to BMS |
| 19 | SUNDAY |  |
| 20 | DIWALI HOLIDAY |  |
| 21 | DIWALI HOLIDAY |  |
| 22 | GOVARDHAN POOJA |  |
| 23 | BHAI DOOJ |  |
| 24 | Aligned PoC of BMS with its respective As-Is report, FRS and SRS. | Team working on PoC for module- Beneficiary Management System, 1) Created Summary of Design and next step definition 2) Finalized PoC for Beneficiary Management System |
| 25 | Conducted internal review for PoC of Beneficiary Management System | Team started working on PoC for module- Training Management System, 1) Structuring LokOS integration and block wise SHG retrieval 2) Discussion for User Interface technology stack most fitting to User requirements |
| 26 | SUNDAY |  |
| 27 | Conducted a client meeting with ‘Training Management’ Thematic experts for resolution of doubts regarding HRA, TA/DA Formats | Team working on PoC for module- Training Management System, 1) Creation of HTML Based UI Wireframe of BMMU and DMMU level Pages 2) Structuring linking of block level Training request modules |
| 28 | CHATH POOJA |  |
| 29 | Conducted an internal strategy meeting regarding State level - Analytics-section of TMS | Team working on PoC for module- Training Management System, 1) Creation of HTML based UI Wireframe of Training Partner and Contact person level Pages |
| 30 | Aligned PoC of TMS with its respective As-Is report, FRS and SRS. | Team working on PoC for module- Training Management System, 1) Created Summary of Design and next step definition 2) Finalized PoC for Training Management System |
| 31 | Conducted internal review for PoC of Training Management System | Team started working on PoC for module- CRP-EP App, 1) Structuring UI Wireframe of Login and CRP Dashboard pages. 2) Discussion for User Interface technology stack most fitting to User requirements |

| Meetings Attended: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| S.No | Meeting Date | Agenda | Participants | Decisions | Conclusions |
| 1 | 09-10-2025 | Submission of FRS documents of all related modules | MD Maam, Janmejay Shukla (JMD), Niti Shrivastav (JMD), and staff | Using the approved baseline of As-Is map and FRS, Team may start working on SRS of all related modules. The FRS of Lakhpati Didi Module shall be kept on hold as the technical understanding of AEP, and VPRP plan from LokOS master data is currently un-available. | Confirmation of approval of all submitted FRS documents of all related modules. |
| 2 | 18-10-2025 | Submission of SRS documents of all related modules | MD Ma’am, Janmejay Shukla (JMD), Niti Shrivastav (JMD), and staff | The team has received an official GO for the development of modules - Beneficiary Management System (BMS), Training Management System (TMS), and Enterprise Sakhi Management System (EPSMS). | Confirmation of approval of all submitted SRS documents of all related modules. |

| Attendance Sheet |  |  |  |  | Oct-25 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date | Day | Sachin Kumar | Akash Tiwari | Pallavee Singh | Ayush M Srivastava | Shilpi Raizada | Harpriya Sharma |
| 01-10-25 | Wed | Present | Present | Present | Present | Present | Present |
| 02-10-25 | Thu | Present | Present | Present | Present | Present | Present |
| 03-10-25 | Fri | Present | Present | Present | Present | Present | Present |
| 04-10-25 | Sat | Present | Present | Present | Present | Present | Present |
| 05-10-25 | Sun | - | - | - | - | - | - |
| 06-10-25 | Mon | Present | Present | Present | Present | Present | Present |
| 07-10-25 | Tue | Present | Present | Present | Present | Present | Present |
| 08-10-25 | Wed | Present | Present | Present | Present | Present | Present |
| 09-10-25 | Thu | Present | Present | Present | Present | Present | Present |
| 10-10-25 | Fri | Present | Present | Present | Present | Present | Present |
| 11-10-25 | Sat | Present | Present | Present | Present | Present | Present |
| 12-10-25 | Sun | - | - | - | - | - | - |
| 13-10-25 | Mon | Present | Present | Present | Present | Present | Present |
| 14-10-25 | Tue | Present | Present | Present | Present | Present | Present |
| 15-10-25 | Wed | Present | Present | Present | Present | Present | Present |
| 16-10-25 | Thu | Present | Present | Present | Present | Present | Present |
| 17-10-25 | Fri | Present | Present | Present | Present | Present | Present |
| 18-10-25 | Sat | Present | Present | Present | Present | Present | Present |
| 19-10-25 | Sun | - | - | - | - | - | - |
| 20-10-25 | Mon | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday |
| 21-10-25 | Tue | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday |
| 22-10-25 | Wed | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday |
| 23-10-25 | Thu | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday |
| 24-10-25 | Fri | Present | Present | Present | Present | Present | Present |
| 25-10-25 | Sat | Present | Present | Present | Present | Present | Present |
| 26-10-25 | Sun | - | - | - | - | - | - |
| 27-10-25 | Mon | Present | Present | Present | Present | Present | Present |
| 28-10-25 | Tue | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday |
| 29-10-25 | Wed | Present | Present | Present | Present | Present | Present |
| 30-10-25 | Thu | Present | Present | Present | Present | Present | Present |
| 31-10-25 | Fri | Present | Present | Present | Present | Present | Present |