## Project Plan Revised
|  | Project Plan for PMU for the Development of an Integrated MIS for effective implementation and Monitoring of Programs under UPSRLM, Lucknow | Document No. |  | BDO/P/UPSRLM/01 | BDO India LLP
|  |  | Rev. No. |  | 1
# | WBS | Task Name | Resource Name | Start Date | End Date | Days | Status | Remark
1 | 1 | Project Start Date | PMU | 2025-09-08 | 2028-09-08 | 1096 | Ongoing | -
2 | 2 | Project UPSRLM Implementation_Pilot Go-Live | PMU | 2025-09-08 | 2028-09-08 | 1096 | Ongoing | -
3 | 2.1 | Project Preparation | PMU |  |  | 0 | Completed | -
4 | 2.1.1 | Project Charter and Governance | PMU | 2025-09-12 | 2025-09-15 | 3 |  | -
5 | 2.1.1.1 | Define Project Goals and Objectives | PMU | 2025-09-12 | 2025-09-15 | 3 | Completed | -
6 | 2.1.1.2 | Organisation Structure,Committees & Standards | PMU | 2025-09-12 | 2025-09-15 | 3 | Completed | -
7 | 2.1.1.3 | Stakeholder and Committee Identification | PMU | 2025-09-12 | 2025-09-15 | 3 | Completed | -
8 | 2.1.1.4 | Communication Management Plan | PMU | 2025-09-12 | 2025-09-15 | 3 | Completed | -
9 | 2.1.1.5 | Risk & Escalation Framework | PMU | 2025-09-12 | 2025-09-15 | 3 | Completed | -
10 | 2.1.2 | Team Mobilisation and Onbaording | PMU | 2025-09-08 | 2025-09-08 | 0 |  | -
11 | 2.1.2.1 | Identify and arrnage Infracture for Project Team | PMU | 2025-09-08 | 2025-09-08 | 0 | Completed | -
12 | 2.1.2.2 | Onboarding Project Team and signoff | UPSRLM & PMU | 2025-09-08 | 2025-09-08 | 0 | Submitted | -
13 | 2.1.3 | AS-IS & Security Study | PMU | 2025-09-15 | 2025-09-20 | 5 |  | -
14 | 2.1.3.1 | Requirement Gathering Workshop and Sign-off -Monitoring through Reports/Dashboards Version 1 | PMU & UPSRLM | 2025-09-15 | 2025-09-17 | 2 | Completed | -
15 | 2.1.3.2 | Requirement Gathering Workshop and Sign-off -Benificiary/User management Version 1 | PMU & UPSRLM | 2025-09-15 | 2025-09-17 | 2 | Completed | -
16 | 2.1.3.3 | Requirement Gathering Workshop and Sign-off -Training Management System Version 1 | PMU & UPSRLM | 2025-09-15 | 2025-09-17 | 2 | Completed | -
17 | 2.1.3.4 | Requirement Gathering Workshop and Sign-off -Enterprise Sakhi Management System Version 1 | PMU & UPSRLM | 2025-09-15 | 2025-09-17 | 2 | Completed | -
18 | 2.1.3.5 | Requirement Gathering Workshop and Sign-off -Lakhpati Didi Management System Version 1 | PMU & UPSRLM | 2025-09-15 | 2025-09-17 | 2 | Completed | -
19 | 2.1.3.7 | Release Draft Version of AS-IS Documents for review | PMU | 2025-09-17 | 2025-09-17 | 0 | Submitted | -
20 | 2.1.3.8 | Review and adopt recommendation - Final Version AS-IS Document for Review - all modules | PMU | 2025-09-17 | 2025-09-17 | 0 | Submitted | -
21 | 2.1.3.9 | Release Draft Version of AS-IS Document and Sign-off -Monitoring through Reports/Dashboards Version 2 | PMU & UPSRLM | 2025-09-17 | 2025-09-20 | 3 | Completed | -
22 | 2.1.3.10 | Release Draft Version of AS-IS Document and Sign-off -Benificiary/User management Version 2 | PMU & UPSRLM | 2025-09-17 | 2025-09-20 | 3 | Completed | -
23 | 2.1.3.11 | Release Draft Version of AS-IS Document and Sign-off -Training Management System Version 2 | PMU & UPSRLM | 2025-09-17 | 2025-09-20 | 3 | Completed | -
24 | 2.1.3.12 | Release Draft Version of AS-IS Document and Sign-off -Enterprise Sakhi Management System Version 2 | PMU & UPSRLM | 2025-09-17 | 2025-09-20 | 3 | Completed | -
25 | 2.1.3.13 | Release Draft Version of AS-IS Document and Sign-off -Lakhpati Didi Management System Version 2 | PMU & UPSRLM | 2025-09-17 | 2025-09-20 | 3 | Completed | -
26 | 2.1.3.14 | Sign off Final Version of AS-IS Documents of all modules | PMU & UPSRLM | 2025-09-20 | 2025-09-20 | 0 | Submitted | -
27 | 2.1.5 | System Analysis and Design(To-Be Process) Workshops - | PMU | 2025-09-21 | 2025-10-20 | 29 |  | -
28 | 2.1.5.1 | FRS Documentation-Beneficiary Management System | PMU | 2025-09-21 | 2025-10-09 | 18 | Completed | -
29 | 2.1.5.2 | FRS Documentation-Training Management System | PMU | 2025-09-21 | 2025-10-09 | 18 | Completed | -
30 | 2.1.5.3 | FRS Documentaion -Enterprise Sakhi Management System | PMU | 2025-09-21 | 2025-10-09 | 18 | Completed | -
31 | 2.1.5.4 | FRS Documentaion -Monitoring through Reports/Dashboards |  | 2025-09-20 |  |  | On Hold by Department | FRS of Power BI Dashboard Module shall be kept on hold as the official handover sessions need to be scheduled by the GDI team
32 | 2.1.5.5 | FRS Documentation -Lakhpati Didi Management System |  | 2025-10-09 |  |  | On Hold by Department | FRS of Lakhpati Didi Module shall be kept on hold as the technical understanding of AEP, and VPRP plan from LokOS master data is currently un-available
33 | 2.1.5.6 | Finalise FRS Sign-off-All Modules | UPSRLM & PMU | 2025-09-21 | 2025-10-09 | 18 | Completed | -
34 | 2.1.5.7 | SRS Documentation-Beneficiary Management System | PMU | 2025-10-10 | 2025-10-20 | 10 | Completed | -
35 | 2.1.5.8 | SRS Documentation-Training Management System | PMU | 2025-10-10 | 2025-10-20 | 10 | Completed | -
36 | 2.1.5.9 | SRS Documentaion -Enterprise Sakhi Management System | PMU | 2025-10-10 | 2025-10-20 | 10 | Completed | -
37 | 2.1.5.10 | Finalise SRS Sign-off-All Modules | UPSRLM & PMU | 2025-10-10 | 2025-10-20 | 10 | Submitted | -
38 | 2.1.5.11 | PoC Documentation-Beneficiary Management System | PMU | 2025-10-21 | 2025-10-24 | 4 | Completed
39 | 2.1.5.12 | PoC Documentation-Training Management System | PMU | 2025-10-25 | 2025-10-30 | 6 | Completed
40 | 2.1.5.13 | PoC Documentation-Enterprise Sakhi Management System | PMU | 2025-10-31 | 2025-11-03 | 5 | Completed
41 | 2.1.5.14 | Finalize PoC Sign-off-All Modules | UPSRLM & PMU | 2025-10-20 | 2025-11-04 | 15 | Submitted
42 | 2.1.6 | System Development |  | 2025-12-07 | 2026-03-17 | 100 | Ongoing | -
43 | 2.1.6.1 | Create Master data for all Modules with scalability | PMU |  |  |  | Ongoing | -
44 | 2.1.6.2 | Coding--Beneficiary Management System | PMU |  |  |  | Ongoing | -
45 | 2.1.6.3 | Coding--Training Management System | PMU |  |  |  | Ongoing | -
46 | 2.1.6.4 | Coding--Enterprise Sakhi Management System | PMU |  |  |  | Ongoing | -
47 | 2.1.6.5 | Integration of all modules | PMU |  |  |  | Ongoing | -
48 | 2.1.7 | Testing |  | 2026-03-20 | 2026-04-19 | 30 | Planned | -
49 | 2.1.7.1 | QA Testing | PMU |  |  |  | Planned | -
50 | 2.1.7.2 | Functional Testing | PMU |  |  |  | Planned | -
51 | 2.1.7.3 | User Inerface Testing | PMU |  |  |  | Planned | -
52 | 2.1.7.4 | Usability Testing | PMU |  |  |  | Planned | -
53 | 2.1.7.5 | Compatibility Testing | PMU |  |  |  | Planned | -
54 | 2.1.7.6 | Performance Testing | PMU |  |  |  | Planned | -
55 | 2.1.7.7 | Security Testing | PMU |  |  |  | Planned | -
56 | 2.1.7.8 | UAT Report | PMU & UPSRLM |  |  |  | Planned | -
57 | 2.1.7.9 | Prepared SOP of all modules | PMU |  |  |  | Planned | -
58 | 2.1.8 | Training |  | 2026-04-20 | 2026-05-20 | 30 | Planned | -
59 | 2.1.8.1 | Training Needs Assessment | PMU |  |  |  | Planned | -
60 | 2.1.8.2 | Training Material Development | PMU |  |  |  | Planned | -
61 | 2.1.8.3 | ToT Program | PMU |  |  |  | Planned | -
62 | 2.1.8.4 | State/District/Block Trainings | PMU |  |  |  | Planned | -
63 | 2.1.8.5 | Training Report & Sign-off | PMU & UPSRLM |  |  |  | Planned | -
64 | 2.1.9 | Go-Live |  | 2026-05-31 | 2026-06-15 | 15 | Planned | -
65 | 2.1.9.1 | Go-Live Readiness Review | PMU |  |  |  | Planned | -
66 | 2.1.9.2 | Pilot Go-Live | PMU |  |  |  | Planned | -
67 | 2.1.9.3 | Pilot Stabilisation | PMU |  |  |  | Planned | -
68 | 2.1.9.4 | Statewide Rollout & Sign-off | PMU & UPSRLM |  |  |  | Planned | -
69 | 2.1.10 | O&M Phase |  | 2026-06-15 | 2028-09-08 | 816 | Planned | -
70 | 2.1.10.1 | Application Support (L1-L3) | PMU |  |  |  | Planned | -
71 | 2.1.10.2 | Quality Management | PMU |  |  |  | Planned | -
72 | 2.1.10.3 | Risk & Issue Management | PMU |  |  |  | Planned | -
73 | 2.1.10.4 | Compliance & Legal Reporting | PMU |  |  |  | Planned | -
74 | 2.1.10.5 | BCP & Disaster Recovery | PMU |  |  |  | Planned | -
75 | 2.1.10.6 | Knowledge Transfer & Exit | PMU |  |  |  | Planned | -
Formulas:
BDO/P/UPSRLM/01 = [Start Date]+3