## Feb 2026
SR# | Activity | Status | Category | Delivery Date | Assigned To | Comments
1 | SUNDAY
2 | Switched to LDMS, (1) Started development of backend for LDMS Department and Schemes Digital Diary | Ongoing | LDMS | 2026-03-09 | Ayush M Srivastava | Worked on designing and implementing APIs, managing databases, and ensuring seamless integration of department schemes. Built the backend using Django with MySQL as the database, focusing on efficient data handling, user management, and secure access control. Collaborated with the frontend team to ensure smooth interaction between the web interface and backend services.
3 | Switched to LDMS, (1) Developing LDMS Department Digital Diary API structure and optimization for smoother and faster responses | Ongoing | LDMS | 2026-03-10 | Ayush M Srivastava | Focused on designing and optimizing APIs to ensure faster, smoother, and more efficient responses. Implemented using Django with MySQL, emphasizing performance, scalability, and secure data handling. Collaborated with the frontend team to maintain seamless integration and improve overall user experience.
4 | Switched to LDMS, (1) Developing LDMS Department Digital Diary APIs and linking with Database | Ongoing | LDMS | 2026-03-11 | Ayush M Srivastava | Developing robust backend APIs for the LDMS Department Digital Diary, ensuring smooth interaction between the application and MySQL database. Focused on designing efficient API structures for secure data access, retrieval, and storage. Implemented using Django, with attention to performance optimization, scalability, and reliable integration with other system components.
5 | Switched to LDMS, (1) Developing LDMS Department UI and flowing Book Animation for scheme browsing per department | Ongoing | LDMS | 2026-03-12 | Ayush M Srivastava | Designed and developed the frontend UI for the LDMS Department Digital Diary, incorporating interactive book-style animations for seamless scheme browsing per department. Implemented using HTML, CSS, JavaScript, and integrated with backend APIs for dynamic content rendering. Focused on enhancing user experience, responsiveness, and intuitive navigation.
6 | Switched to LDMS, (1) Integrating the LDMS Department Digital Diary component in Pragati-Setu LDMS Module | Ongoing | LDMS | 2026-03-13 | Ayush M Srivastava | Integrated the LDMS Digital Diary component into the Pragati-Setu LDMS Module, ensuring smooth data flow between modules. Coordinated backend API endpoints and frontend UI elements to maintain seamless functionality. Worked with Django and MySQL, optimizing for consistent performance and reliability across the integrated system.
7 | Switched to LDMS, (1) Integrating the LDMS Department Digital Diary component with the Support Bucket Recommendation System | Ongoing | LDMS | 2026-03-14 | Ayush M Srivastava | Integrated the LDMS Digital Diary with the Support Bucket Recommendation System to enable real-time scheme suggestions. Focused on backend logic, API connections, and data consistency using Django and MySQL. Ensured secure, fast, and accurate recommendations while maintaining smooth interaction with other system modules.
8 | SUNDAY
9 | Switched to LDMS, (1) Solving bugs related to the Support Bucket Recommendation System and migrating the project to Internal testing server for preparation for Presentation at UPSRLM HQ | Completed | LDMS | 2026-03-09 | Ayush M Srivastava | Identified and resolved critical bugs in the Support Bucket Recommendation System to ensure accurate recommendations. Migrated the LDMS project to the internal testing server, ensuring stable deployment and smooth functionality in preparation for a high-level presentation at UPSRLM HQ. Coordinated backend and frontend fixes using Django and MySQL, maintaining system reliability.
10 | Switched to LDMS, (1) Final Testing and implementation of speed-loading optimization of Digital Diary UI and Support Bucket Recommendation System | Completed | LDMS | 2026-03-10 | Ayush M Srivastava | Conducted thorough final testing of the Digital Diary UI and Support Bucket Recommendation System, implementing optimizations for faster page load and response times. Focused on enhancing performance, reducing latency, and ensuring seamless user experience. Utilized Django, MySQL, and frontend optimization techniques to achieve efficient system performance.
11 | Presented First Demo of Lakhpati Didi Management System (v0.1) to MD Maam and other Stakeholders in UPSRLM HQ | Completed | LDMS | 2026-03-11 | Ayush M Srivastava | Delivered the first functional demo of the Lakhpati Didi Management System (v0.1) to MD Ma’am and key stakeholders at UPSRLM HQ. Showcased core features, interactive UI, and backend functionality, highlighting performance improvements and integrated modules. Received feedback to guide further development and enhancements.
12 | Switched to EPSMS, (1) Strengthening the Security procedures regarding CRP-EP App and preparaing for Round 1 of External Testing | Ongoing | CRP-EP App | 2026-03-16 | Ayush M Srivastava | Enhanced security measures for the CRP-EP App, focusing on user authentication, data integrity, and access control. Prepared the application for Round 1 of external testing by ensuring compliance with security protocols, testing for vulnerabilities, and implementing best practices. Worked with backend systems using Django and database management in MySQL.
13 | On Leave due to Family emergency
14 | Switched to EPSMS, (1) Working on Google Play Console metadata for UPSRLM Development Account and preparing Android Package (signed release) for uploading on Google Play Console | Ongoing | CRP-EP App | 2026-03-16 | Ayush M Srivastava | Managed the Google Play Console setup for the UPSRLM Development Account, including preparing all required app metadata, descriptions, and assets. Built and configured the signed Android release package (APK/AAB) for secure upload to the Play Store. Ensured proper versioning, compliance with Play Store policies, and smooth deployment for internal and external testing.
15 | SUNDAY
16 | Went to UPSRLM for completion of registration of Google Play console account and UPSRLM ID related documents upload | Ongoing | CRP-EP App | 2026-03-17 | Ayush M Srivastava | Visited UPSRLM HQ to complete the registration process for the Google Play Console account. Uploaded all required organizational and personal documents to ensure account verification and compliance with Play Store requirements. Coordinated with UPSRLM officials to verify credentials and streamline the app deployment process.
17 | Went to UPSRLM for resolving issue of ID verification gplay console and sent the android app to Round 1 of external Audit | Completed | CRP-EP App | 2026-03-17 | Ayush M Srivastava | Resolved ID verification issues with the Google Play Console in coordination with UPSRLM officials. Ensured the Android app met all verification and compliance requirements, and successfully submitted the app for Round 1 of external audit. Monitored the submission to guarantee proper deployment and testing readiness.
18 | Moved to NIC Team of Developers for SNA Sparsh Portal | Ongoing | SNA-Sparsh | 2026-03-25 | Ayush M Srivastava
19 | Moved to NIC Team of Developers for SNA Sparsh Portal | Ongoing | SNA-Sparsh | 2026-03-25 | Ayush M Srivastava
20 | Moved to NIC Team of Developers for SNA Sparsh Portal | Ongoing | SNA-Sparsh | 2026-03-25 | Ayush M Srivastava
21 | Moved to NIC Team of Developers for SNA Sparsh Portal | Ongoing | SNA-Sparsh | 2026-03-25 | Ayush M Srivastava
22 | SUNDAY
23 | Moved to NIC Team of Developers for SNA Sparsh Portal | Ongoing | SNA-Sparsh | 2026-03-25 | Ayush M Srivastava
24 | Moved to NIC Team of Developers for SNA Sparsh Portal | Ongoing | SNA-Sparsh | 2026-03-25 | Ayush M Srivastava
25 | Moved to NIC Team of Developers for SNA Sparsh Portal | Completed | SNA-Sparsh | 2026-03-25 | Ayush M Srivastava
26 | Switched to EPSMS, (1) Fixing Vulnerabilities of CRP-EP App observed in the 1st round of audit of CRP-EP App | Ongoing | CRP-EP App | 2026-03-28 | Ayush M Srivastava | Identified and resolved security vulnerabilities reported during the first audit of the CRP-EP App. Implemented backend and frontend fixes to strengthen authentication, data handling, and access control. Ensured compliance with security best practices to pass subsequent audit rounds and improve overall app reliability.
27 | Switched to EPSMS, (1) Resolving IDOR error observed in Different APIs and recorded evidence for Audit response report | Ongoing | CRP-EP App | 2026-03-29 | Ayush M Srivastava | Fixed IDOR (Insecure Direct Object Reference) issues in multiple APIs to prevent unauthorized access. Conducted thorough testing and documented evidence of resolutions for the audit response report. Enhanced API security and ensured the app complied with strict data access protocols.
28 | Switched to EPSMS, (1) Addition of Base64 based cache encryption and decryption protocols at Application Layer in CRP-EP Android App | Completed | CRP-EP App | 2026-03-30 | Ayush M Srivastava | Implemented Base64-based encryption and decryption protocols at the application layer to secure cached data in the CRP-EP Android App. Improved data privacy and reduced risks of sensitive information exposure. Ensured seamless integration with existing app functionality without affecting performance.
29 | SUNDAY
30 | On Leave due to stomach infection
31 | Switched to TMS, (1) Started working on Training Partner Contact Person bug observerd in internal UAT | Ongoing | TMS | 2026-04-04 | Ayush M Srivastava | Investigated and resolved a bug related to Training Partner Contact Person functionality discovered during internal UAT of the TMS module. Debugged backend logic and fixed data handling issues using Django and MySQL to ensure accurate assignment and display of contact persons. Verified the fix through testing to maintain system reliability and smooth user experience.